Final financial Report for Advocacy Campaign budget for MTT8 follow-up (TMAP/ITPC) 01 April 2010 - 31 March 2011

Society Association HIV.LV, Latvia

| Category of Expenditure | Responsibilities / activity record | Total amount, LVL, planned | Total amount, USD, planned | Spent, LVL | Spent, USD |
| --- | --- | --- | --- | --- | --- |
| 1. Project personnel (salaries, all taxes included) |  | 1940,00 | 3779,00 | 1940,00 | 3778,74 |
| 1.1. Head of the project (overhead) | Project coordination, organizing of measures, advocacy work | 672,00 |  | 672,00 | 1308,92 |
| 1.2. Defender of the interests of PLHIV | Organizing of measures, advocacy work | 672,00 |  | 672,00 | 1308,92 |
| 1.3. External consultant and methodology developer | Consultations, questionnaires, surveys | 200,00 |  | 200,00 | 389,56 |
| 1.4. Accountant of the project | Accountancy of the project / lawyer | 216,00 |  | 216,00 | 420,74 |
| 1.5. Reward for participation in working group meetings for representatives from partner NGO-s |  | 180,00 |  | 180,00 | 350,60 |
| 2. Round tables, press conferences |  | 526,00 | 1024,00 | 513,82 | 1000,82 |
| 2.1. Handouts of materials while round tables and working groups | 12 measures / 10 participant in each | 84,00 |  | 84,00 | 163,62 |
| 2.2. Handouts of materials for journalists | 2 press conferences / 12 journalists in each | 36,00 |  | 36,00 | 70,12 |
| 2.3. Coffee breaks while working groups, and round tables, and press conferences | 14 measures / 10 - 12 participant in each | 210,00 |  | 197,81 | 385,29 |
| 2.4. Space rental costs on all measures | To be paid for hosting organisation | 196,00 |  | 196,01 | 381,79 |
| 2A Printed materials | A brochure with 2 Reports: MTT8 Latvia's chapter and Alternative UNGASS in Latvian - budget changes reported in interim report | 109,70 | 214,00 | 109,70 | 213,67 |
| 3. Travel costs | Budget changes reported in interim report | 100,30 | 195,00 | 111,70 | 217,57 |
| Travel costs to the generic drug manufacturers representatives, Central WHO office in Baltics, visiting expert from EHRN (Lithuania) | Travel to Vilnius and Kaunas | 100,30 |  | 111,70 | 217,57 |
| 4. Organisation's web-site |  | 169,18 | 330,00 | 169,17 | 329,50 |
| Maintenance of organisation's internet web-page www.apvienibahiv.lv as advocacy instrument | Association's HIV.LV web-page www.apvienibahiv.lv | 169,18 |  | 169,17 | 329,50 |
| 5. Other administrative costs |  | 235,22 | 458,00 | 236,01 | 459,70 |
| 5.1. Stationery | Association HIV.LV | 48,00 |  | 46,77 | 91,10 |
| 5.2. Telephone | Association HIV.LV | 180,00 |  | 181,24 | 353,02 |
| 5.3. Bank expences | Association HIV.LV | 7,22 |  | 8,00 | 15,58 |
| Total budget: | currency exchange rate 01.04.2010 1 USD = 0,51340 LVL, Swedbank AS | 3080,40 | 6000,00 | 3080,40 | 6000,00 |

Chairman of the Board                                                                                                                                      Aleksandrs Molokovskis

04 April, 2011